## Dashboard
Project Management Dashboard |  |  |  |  | 17-Feb-22 to 8-Apr-22
Project | Task | Manager | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14
Alpha | Task 1 | McFay | 2022-03-21 | 2022-03-30 | 8 | 3 | 37.5% | 96000 | 32256
| Task 2 | Wood | 2022-03-22 | 2022-04-01 | 9 | 4 | 44.44% | 513000 | 226233
| Task 3 | Ladd | 2022-03-23 | 2022-03-29 | 5 | 3 | 60% | 616000 | 401579
| Task 4 | Hirsch | 2022-03-24 | 2022-03-28 | 3 | 3 | 100% | 817000 | 807069
| Task 5 | Samora | 2022-03-25 | 2022-04-04 | 7 | 3 | 42.86% | 372000 | 173166
| Task 6 | McFay | 2022-03-26 | 2022-04-08 | 10 | 2 | 20% | 50000 | 8400
| Task 7 | Wood | 2022-03-27 | 2022-04-08 | 10 | 3 | 30% | 807000 | 262679
| Task 8 | Ladd | 2022-03-28 | 2022-03-30 | 3 | 0 | 0% | 691000 | 0
Delta | Task 1 | Hirsch | 2022-03-14 | 2022-03-24 | 9 | 8 | 88.89% | 787000 | 727188
| Task 2 | Samora | 2022-03-15 | 2022-03-28 | 10 | 2 | 20% | 228000 | 47880
| Task 3 | McFay | 2022-03-16 | 2022-03-21 | 4 | 0 | 0% | 147000 | 0
| Task 4 | Wood | 2022-03-17 | 2022-03-28 | 8 | 5 | 62.5% | 338000 | 205123
| Task 5 | Ladd | 2022-03-18 | 2022-03-31 | 10 | 3 | 30% | 857000 | 305949
| Task 6 | Hirsch | 2022-03-19 | 2022-03-28 | 6 | 3 | 50% | 602000 | 322371
| Task 7 | Samora | 2022-03-20 | 2022-03-24 | 4 | 2 | 50% | 990000 | 451440
Gemini | Task 1 | Hirsch | 2022-02-17 | 2022-02-23 | 5 | 2 | 40% | 218000 | 97337
| Task 2 | Samora | 2022-02-18 | 2022-02-25 | 6 | 3 | 50% | 393000 | 177440
| Task 3 | McFay | 2022-02-19 | 2022-03-04 | 10 | 4 | 40% | 86000 | 31046
| Task 4 | Wood | 2022-02-20 | 2022-03-03 | 9 | 3 | 33.33% | 732000 | 261324
| Task 5 | Ladd | 2022-02-21 | 2022-02-24 | 4 | 1 | 25% | 492000 | 116850
| Task 6 | Hirsch | 2022-02-22 | 2022-03-01 | 6 | 0 | 0% | 188000 | 0
| Task 7 | Samora | 2022-02-23 | 2022-03-03 | 7 | 3 | 42.86% | 180000 | 79380
| Task 8 | McFay | 2022-02-24 | 2022-03-02 | 5 | 2 | 40% | 582000 | 195231
| Task 9 | Wood | 2022-02-25 | 2022-03-09 | 9 | 1 | 11.11% | 562000 | 74746
| Task 10 | Ladd | 2022-02-26 | 2022-03-07 | 6 | 3 | 50% | 416000 | 175015
Orion | Task 1 | Hirsch | 2022-02-27 | 2022-03-08 | 7 | 7 | 100% | 293000 | 273001
| Task 2 | Samora | 2022-02-28 | 2022-03-10 | 9 | 4 | 44.44% | 224000 | 57910
| Task 3 | McFay | 2022-03-01 | 2022-03-10 | 8 | 0 | 0% | 978000 | 0
| Task 4 | Wood | 2022-03-02 | 2022-03-10 | 7 | 3 | 42.86% | 932000 | 379157
| Task 5 | Ladd | 2022-03-03 | 2022-03-08 | 4 | 1 | 25% | 854000 | 322812
| Task 6 | Hirsch | 2022-03-04 | 2022-03-11 | 6 | 3 | 50% | 81000 | 38461
| Task 7 | Samora | 2022-03-05 | 2022-03-14 | 6 | 5 | 83.33% | 169000 | 136468
| Task 8 | McFay | 2022-03-06 | 2022-03-10 | 4 | 1 | 25% | 61000 | 12078
| Task 9 | Wood | 2022-03-07 | 2022-03-15 | 7 | 3 | 42.86% | 645000 | 273048
| Task 10 | Ladd | 2022-03-08 | 2022-03-10 | 3 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Hirsch | 2022-03-09 | 2022-03-22 | 10 | 5 | 50% | 839000 | 406974
| Task 2 | Samora | 2022-03-10 | 2022-03-16 | 5 | 4 | 80% | 729000 | 487139
| Task 3 | McFay | 2022-03-11 | 2022-03-21 | 7 | 3 | 42.86% | 826000 | 298186
| Task 4 | Wood | 2022-03-12 | 2022-03-22 | 7 | 2 | 28.57% | 895000 | 280583
| Task 5 | Ladd | 2022-03-13 | 2022-03-16 | 3 | 2 | 66.67% | 341000 | 129785
Grand Total | [7 empty] | 19695000 | 8340291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
42%

## Workings
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 4 | =COUNTIF(Dashboard!H6:H51,"="&0) | Values |  | Doughnut Chart | % | Formula | 0
Bar Chart | 8340291 | 19695000 | In Progress | 33 | =COUNTIFS(Dashboard!H6:H51,"<>"&0,Dashboard!H6:H51,"<"&1) | Days completed | 112 | Days Completed | 42.11% | =J3/$J$4
Dougnut Chart | 42.35% | 57.65% | Completed | 3 | =COUNTIF(Dashboard!H6:H51,"="&1) | Duration | 266 | Days Remaining | 57.89% | =1-M3
|  | =1-B4 | Remaining | 37 | =F3+F2
|  |  | Total Tasks | 40 | =COUNTA(Dashboard!B6:B50)

## Instructions
Project Management Dashboard Instructions
Step 1 | Format source data in an Excel Table - CTRL+T
Step 2 | Dashboard PivotTable
2.01 | Insert Dashboard PivotTable in cell A5
2.02 | Format PivotTable with Tabular layout & no subtotals
2.03 | Format PivotTable Budget & Actual values via Field Settings
2.04 | PivotTable Options > Turn off Expand/Collapse buttons
2.05 | Format PivotTable in light grey
Step 3 | Insert Table for Tasks Bar Chart on Workings Sheet
Bar chart height 3.73 x 9.0 wide.
Step 4 | Insert doughnut chart PivotTable for Overall Completed - Completed Days vs Duration
Chart height 3.73 x width 3.25
Step 5 | Insert budget vs actual doughnut & bar chart PivotTable on Workings Sheet
Doughnut hole 58%
Bar chart series overlap -30%, gap width 0%
Doughnut chart height 3.73 x width 3.25, Bar Chart height 3.73 x width 6.
Step 6 | Insert Slicers for Project and Manager fields & connect to all PivotTables
Step 7 | Add text for date range to header cell F1:
=TEXT(MIN(D6:D51),"d-mmm-yy")&" to "&TEXT(MAX(E6:E51),"d-mmm-yy")
Step 8 | Add scroll bar and link to a cell P2 in the Workings sheet
Step 9 | Add calendar dates in cell K5:AJ5
Note: the formula below only works in Excel for Office 365.
=SEQUENCE(1,26,MIN(Table1[Start Date])+Workings!P2,1)
Step 10 | Gantt Chart - Conditional Formatting (extend the 'applies to' range to allow for growth in your data)
10.1 | Add data bars to Progress column of PivotTable
10.2 | Format Dates in row 5
10.3 | Shade columns for weekend dates
10.4 | Add fill colour for completed dates
10.5 | Add fill colour for in progress dates
10.6 | Add cell borders for 'not started' dates
10.7 | Add grey shading to Grand Total row
Step 11 | Freeze Panes at cell A6

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Project 1 | Task 1 | McFay | 2022-03-21 | 8 | 2022-03-30 | 3 | 37.5% | 96000 | 32256
Project 1 | Task 2 | Wood | 2022-03-22 | 9 | 2022-04-01 | 4 | 44.44% | 513000 | 226233
Project 1 | Task 3 | Ladd | 2022-03-23 | 5 | 2022-03-29 | 3 | 60% | 616000 | 401579
Project 1 | Task 4 | Hirsch | 2022-03-24 | 3 | 2022-03-28 | 3 | 100% | 817000 | 807069
Project 1 | Task 5 | Samora | 2022-03-25 | 7 | 2022-04-04 | 3 | 42.86% | 372000 | 173166
Project 1 | Task 6 | McFay | 2022-03-26 | 10 | 2022-04-08 | 2 | 20% | 50000 | 8400
Project 1 | Task 7 | Wood | 2022-03-27 | 10 | 2022-04-08 | 3 | 30% | 807000 | 262679
Project 1 | Task 8 | Ladd | 2022-03-28 | 3 | 2022-03-30 | 0 | 0% | 691000 | 0
Project 2 | Task 1 | Hirsch | 2022-03-14 | 9 | 2022-03-24 | 8 | 88.89% | 787000 | 727188
Project 2 | Task 2 | Samora | 2022-03-15 | 10 | 2022-03-28 | 2 | 20% | 228000 | 47880
Project 2 | Task 3 | McFay | 2022-03-16 | 4 | 2022-03-21 | 0 | 0% | 147000 | 0
Project 2 | Task 4 | Wood | 2022-03-17 | 8 | 2022-03-28 | 5 | 62.5% | 338000 | 205123
Project 2 | Task 5 | Ladd | 2022-03-18 | 10 | 2022-03-31 | 3 | 30% | 857000 | 305949
Project 2 | Task 6 | Hirsch | 2022-03-19 | 6 | 2022-03-28 | 3 | 50% | 602000 | 322371
Project 2 | Task 7 | Samora | 2022-03-20 | 4 | 2022-03-24 | 2 | 50% | 990000 | 451440
Project 3 | Task 1 | Hirsch | 2022-02-17 | 5 | 2022-02-23 | 2 | 40% | 218000 | 97337
Project 3 | Task 2 | Samora | 2022-02-18 | 6 | 2022-02-25 | 3 | 50% | 393000 | 177440
Project 3 | Task 3 | McFay | 2022-02-19 | 10 | 2022-03-04 | 4 | 40% | 86000 | 31046
Project 3 | Task 4 | Wood | 2022-02-20 | 9 | 2022-03-03 | 3 | 33.33% | 732000 | 261324
Project 3 | Task 5 | Ladd | 2022-02-21 | 4 | 2022-02-24 | 1 | 25% | 492000 | 116850
Project 3 | Task 6 | Hirsch | 2022-02-22 | 6 | 2022-03-01 | 0 | 0% | 188000 | 0
Project 3 | Task 7 | Samora | 2022-02-23 | 7 | 2022-03-03 | 3 | 42.86% | 180000 | 79380
Project 3 | Task 8 | McFay | 2022-02-24 | 5 | 2022-03-02 | 2 | 40% | 582000 | 195231
Project 3 | Task 9 | Wood | 2022-02-25 | 9 | 2022-03-09 | 1 | 11.11% | 562000 | 74746
Project 3 | Task 10 | Ladd | 2022-02-26 | 6 | 2022-03-07 | 3 | 50% | 416000 | 175015
Project 4 | Task 1 | Hirsch | 2022-02-27 | 7 | 2022-03-08 | 7 | 100% | 293000 | 273001
Project 4 | Task 2 | Samora | 2022-02-28 | 9 | 2022-03-10 | 4 | 44.44% | 224000 | 57910
Project 4 | Task 3 | McFay | 2022-03-01 | 8 | 2022-03-10 | 0 | 0% | 978000 | 0
Project 4 | Task 4 | Wood | 2022-03-02 | 7 | 2022-03-10 | 3 | 42.86% | 932000 | 379157
Project 4 | Task 5 | Ladd | 2022-03-03 | 4 | 2022-03-08 | 1 | 25% | 854000 | 322812
Project 4 | Task 6 | Hirsch | 2022-03-04 | 6 | 2022-03-11 | 3 | 50% | 81000 | 38461
Project 4 | Task 7 | Samora | 2022-03-05 | 6 | 2022-03-14 | 5 | 83.33% | 169000 | 136468
Project 4 | Task 8 | McFay | 2022-03-06 | 4 | 2022-03-10 | 1 | 25% | 61000 | 12078
Project 4 | Task 9 | Wood | 2022-03-07 | 7 | 2022-03-15 | 3 | 42.86% | 645000 | 273048
Project 4 | Task 10 | Ladd | 2022-03-08 | 3 | 2022-03-10 | 3 | 100% | 68000 | 64987
Project 5 | Task 1 | Hirsch | 2022-03-09 | 10 | 2022-03-22 | 5 | 50% | 839000 | 406974
Project 5 | Task 2 | Samora | 2022-03-10 | 5 | 2022-03-16 | 4 | 80% | 729000 | 487139
Project 5 | Task 3 | McFay | 2022-03-11 | 7 | 2022-03-21 | 3 | 42.86% | 826000 | 298186
Project 5 | Task 4 | Wood | 2022-03-12 | 7 | 2022-03-22 | 2 | 28.57% | 895000 | 280583
Project 5 | Task 5 | Ladd | 2022-03-13 | 3 | 2022-03-16 | 2 | 66.67% | 341000 | 129785
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)