## Dashboard
Project Management Dashboard |  |  |  |  | 17-Feb-20 to 13-Mar-20
Project | Task | Manager | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
Alpha | Task 1 | McFay | 2020-02-28 | 2020-03-10 | 8 | 3 | 37.5% | 96000 | 32256
| Task 2 | Wood | 2020-03-02 | 2020-03-12 | 9 | 4 | 44.44% | 513000 | 226233
| Task 3 | Ladd | 2020-02-20 | 2020-02-26 | 5 | 3 | 60% | 616000 | 401579
| Task 4 | Hirsch | 2020-02-19 | 2020-02-21 | 3 | 3 | 100% | 817000 | 807069
| Task 5 | Samora | 2020-02-21 | 2020-03-02 | 7 | 3 | 42.86% | 372000 | 173166
| Task 6 | McFay | 2020-02-24 | 2020-03-06 | 10 | 2 | 20% | 50000 | 8400
| Task 7 | Wood | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 807000 | 262679
| Task 8 | Ladd | 2020-02-24 | 2020-02-26 | 3 | 0 | 0% | 691000 | 0
Delta | Task 1 | Hirsch | 2020-03-02 | 2020-03-12 | 9 | 8 | 88.89% | 787000 | 727188
| Task 2 | Samora | 2020-03-02 | 2020-03-13 | 10 | 2 | 20% | 228000 | 47880
| Task 3 | McFay | 2020-02-17 | 2020-02-20 | 4 | 0 | 0% | 147000 | 0
| Task 4 | Wood | 2020-02-19 | 2020-02-28 | 8 | 5 | 62.5% | 338000 | 205123
| Task 5 | Ladd | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 857000 | 305949
| Task 6 | Hirsch | 2020-02-25 | 2020-03-03 | 6 | 3 | 50% | 602000 | 322371
| Task 7 | Samora | 2020-02-25 | 2020-02-28 | 4 | 2 | 50% | 990000 | 451440
Gemini | Task 1 | Hirsch | 2020-02-17 | 2020-02-21 | 5 | 2 | 40% | 218000 | 97337
| Task 2 | Samora | 2020-02-17 | 2020-02-24 | 6 | 3 | 50% | 393000 | 177440
| Task 3 | McFay | 2020-02-18 | 2020-03-02 | 10 | 4 | 40% | 86000 | 31046
| Task 4 | Wood | 2020-02-21 | 2020-03-04 | 9 | 3 | 33.33% | 732000 | 261324
| Task 5 | Ladd | 2020-02-17 | 2020-02-20 | 4 | 1 | 25% | 492000 | 116850
| Task 6 | Hirsch | 2020-02-20 | 2020-02-27 | 6 | 0 | 0% | 188000 | 0
| Task 7 | Samora | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 180000 | 79380
| Task 8 | McFay | 2020-02-24 | 2020-02-28 | 5 | 2 | 40% | 582000 | 195231
| Task 9 | Wood | 2020-02-24 | 2020-03-05 | 9 | 1 | 11.11% | 562000 | 74746
| Task 10 | Ladd | 2020-02-24 | 2020-03-02 | 6 | 3 | 50% | 416000 | 175015
Orion | Task 1 | Hirsch | 2020-02-18 | 2020-02-26 | 7 | 7 | 100% | 293000 | 273001
| Task 2 | Samora | 2020-02-17 | 2020-02-27 | 9 | 4 | 44.44% | 224000 | 57910
| Task 3 | McFay | 2020-02-18 | 2020-02-27 | 8 | 0 | 0% | 978000 | 0
| Task 4 | Wood | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 932000 | 379157
| Task 5 | Ladd | 2020-02-21 | 2020-02-26 | 4 | 1 | 25% | 854000 | 322812
| Task 6 | Hirsch | 2020-02-21 | 2020-02-28 | 6 | 3 | 50% | 81000 | 38461
| Task 7 | Samora | 2020-02-24 | 2020-03-02 | 6 | 5 | 83.33% | 169000 | 136468
| Task 8 | McFay | 2020-02-25 | 2020-02-28 | 4 | 1 | 25% | 61000 | 12078
| Task 9 | Wood | 2020-02-27 | 2020-03-06 | 7 | 3 | 42.86% | 645000 | 273048
| Task 10 | Ladd | 2020-02-17 | 2020-02-19 | 3 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Hirsch | 2020-02-17 | 2020-02-28 | 10 | 5 | 50% | 839000 | 406974
| Task 2 | Samora | 2020-02-21 | 2020-02-27 | 5 | 4 | 80% | 729000 | 487139
| Task 3 | McFay | 2020-02-24 | 2020-03-03 | 7 | 3 | 42.86% | 826000 | 298186
| Task 4 | Wood | 2020-02-26 | 2020-03-05 | 7 | 2 | 28.57% | 895000 | 280583
| Task 5 | Ladd | 2020-02-28 | 2020-03-03 | 3 | 2 | 66.67% | 341000 | 129785
Grand Total | [7 empty] | 19695000 | 8340291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
42%

## Workings
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 4 | =COUNTIF(Dashboard!H6:H51,"="&0) | Values |  | Doughnut Chart | % | Formula | 0
Bar Chart | 8340291 | 19695000 | In Progress | 33 | =COUNTIFS(Dashboard!H6:H51,"<>"&0,Dashboard!H6:H51,"<"&1) | Days completed | 112 | Days Completed | 42.11% | =J3/$J$4
Dougnut Chart | 42.35% | 57.65% | Completed | 3 | =COUNTIF(Dashboard!H6:H51,"="&1) | Duration | 266 | Days Remaining | 57.89% | =1-M3
|  | =1-B4 | Remaining | 37 | =F3+F2
|  |  | Total Tasks | 40 | =COUNTA(Dashboard!B6:B50)

## Instructions
Project Management Dashboard Instructions
Step 1 | Format source data in an Excel Table - CTRL+T
Step 2 | Dashboard PivotTable
2.01 | Insert Dashboard PivotTable in cell A5
2.02 | Format PivotTable with Tabular layout & no subtotals
2.03 | Format PivotTable Budget & Actual values via Field Settings
2.04 | PivotTable Options > Turn off Expand/Collapse buttons
2.05 | Format PivotTable in light grey
Step 3 | Insert Table for Tasks Bar Chart on Workings Sheet
Bar chart height 3.73 x 9.0 wide.
Step 4 | Insert doughnut chart PivotTable for Overall Completed - Completed Days vs Duration
Chart height 3.73 x width 3.25
Step 5 | Insert budget vs actual doughnut & bar chart PivotTable on Workings Sheet
Doughnut hole 58%
Bar chart series overlap -30%, gap width 0%
Doughnut chart height 3.73 x width 3.25, Bar Chart height 3.73 x width 6.
Step 6 | Insert Slicers for Project and Manager fields & connect to all PivotTables
Step 7 | Add text for date range to header cell F1:
=TEXT(MIN(D6:D51),"d-mmm-yy")&" to "&TEXT(MAX(E6:E51),"d-mmm-yy")
Step 8 | Add scroll bar and link to a cell P2 in the Workings sheet
Step 9 | Add calendar dates in cell K5:AJ5
Note: the formula below only works in Excel for Office 365.
=SEQUENCE(1,26,MIN(Table1[Start Date])+Workings!P2,1)
Step 10 | Gantt Chart - Conditional Formatting (extend the 'applies to' range to allow for growth in your data)
10.1 | Add data bars to Progress column of PivotTable
10.2 | Format Dates in row 5
10.3 | Shade columns for weekend dates
10.4 | Add fill colour for completed dates
10.5 | Add fill colour for in progress dates
10.6 | Add cell borders for 'not started' dates
10.7 | Add grey shading to Grand Total row
Step 11 | Freeze Panes at cell A6
CLICK TO WATCH THE
VIDEO TUTORIAL

## Dashboard Protection
Protecting your dashboard
2. Worksheet Protection - You'll find the Worksheet Protection on the Review tab:
1. Slicers - prevent users activating the pull handles when using the Slicer by selecting 'Disable resizing and moving' in the Slicer Position and Layout setting (right-click Slicer).
Or Slicers - Simply protect the worksheet containing the Dashboard, but make sure you 'unprotect' Slicers so that they can still be clicked:
Before Disabling Resizing
After Disabling Resizing
If your Dashboard sheet contains a PivotTable, make sure 'Use PivotTable & PivotChart' is checked so that Slicers work.
Note, this will prevent the PivotTables in the entire file from being refreshed, so if you're planning on updating your dashboard with new data, then option 3 is preferred.
4. Protect Workbook
Once you've 'VeryHidden' the sheets containing your workings and data you need to protect your workbook so your users can't unhide them.
WARNING: this protection is not bullet proof. If a user wants to get to your underlying data they can find a way. A Google search will reveal various ways to crack your password, or simply remove the protection.
Therefore Worksheet Protection should be used to prevent users breaking your report, but don't count on it protecting super sensitive information.
3. Hide Worksheets
A better solution is to set the property for the
sheets containing your data and workings to
VeryHidden in the VB Editor Alt+F11.
When you right-click the sheet tab there is no
indication that worksheets are hidden when
their properties are set to 'xlSheetVeryHidden'

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Gemini | Task 1 | Hirsch | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
Gemini | Task 2 | Samora | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
Gemini | Task 3 | McFay | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
Gemini | Task 4 | Wood | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
Gemini | Task 5 | Ladd | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
Gemini | Task 6 | Hirsch | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
Gemini | Task 7 | Samora | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
Gemini | Task 8 | McFay | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
Gemini | Task 9 | Wood | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
Gemini | Task 10 | Ladd | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
Orion | Task 1 | Hirsch | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
Orion | Task 2 | Samora | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
Orion | Task 3 | McFay | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
Orion | Task 4 | Wood | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
Orion | Task 5 | Ladd | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
Orion | Task 6 | Hirsch | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
Orion | Task 7 | Samora | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
Orion | Task 8 | McFay | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
Orion | Task 9 | Wood | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
Orion | Task 10 | Ladd | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Hirsch | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
Vega | Task 2 | Samora | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
Vega | Task 3 | McFay | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
Vega | Task 4 | Wood | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
Vega | Task 5 | Ladd | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
Delta | Task 1 | Hirsch | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
Delta | Task 2 | Samora | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
Delta | Task 3 | McFay | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
Delta | Task 4 | Wood | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
Delta | Task 5 | Ladd | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
Delta | Task 6 | Hirsch | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
Delta | Task 7 | Samora | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
Alpha | Task 1 | McFay | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
Alpha | Task 2 | Wood | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
Alpha | Task 3 | Ladd | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
Alpha | Task 4 | Hirsch | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
Alpha | Task 5 | Samora | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
Alpha | Task 6 | McFay | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
Alpha | Task 7 | Wood | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
Alpha | Task 8 | Ladd | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)